## Sheet1
Team Name: | Amica
Group Members: | Evan Hadinata Ginting (33477558)
Harsh Jain (33397058)
Meeting Details:
Date | Time start | Time end | Members present | Discussions
2023-09-17 | 13:30 | 14:30 | All | - Set up the GitHub repository - Determine the next meeting date
2023-09-19 | 22:00 | 22:30 | All | - Both will prepare Q1 and compare and combine in next meeting. - Deadline for Q1 is 23/09/2023. - Next meeting will be held on 24/09/2023 to combine the Q1 and make plan for the next questions.
2023-09-24 | 19:00 | 21:00 | All | - Committed individual Q1's and combined them - Updated Github - Deadline for Q2 is 25/09/2023 and meeting is also on the same day
2023-09-25 | 20:00 | 21:00 | All | - What needs to be done for the data quality check - Assessing assertion data and event data - Deadline for Q3 part one is 27/09/2023 - Next meeting on 27/09/2023
2023-09-27 | 21:30 | 22:40 | All | - Data quality check finalised - Data cleansing to be for Q3 part 2 - Deadline for Q3 part 2 is 29/09/2023 - Next meeting on 29/09/2023